## Weekly Plan
TiffinBD - 8 Week Project Plan
Duration: April 29 - June 23, 2026 ¦ Total: 8 Weeks
# | Week | Task/Subtask | Description
WEEK 1: Apr 29 - May 5
| 1.1 | Environment & Git Setup | Docker, Node.js, MySQL, version control
| 1.2 | NestJS Backend | Project scaffolding, common modules, logging
| 1.3 | Database Design | MySQL schema, TypeORM entities, migrations
| 1.4 | Docker Setup | Dockerfiles, docker-compose, database container
| 1.5 | Health & Tests | Health endpoint, Jest integration tests
WEEK 2: May 6 - May 12
| 2.1 | Auth Module | JWT tokens, login/refresh/logout endpoints
| 2.2 | RBAC System | 6 roles, permissions, guards, decorators
| 2.3 | Users Management | User CRUD, service, endpoints
| 2.4 | Branch Assignment | User-branch roles, device registration
| 2.5 | Auth Tests | Unit, integration, E2E auth tests
WEEK 3: May 13 - May 19
| 3.1 | Branch Management | Branch CRUD, service, dynamic config
| 3.2 | Connectors Framework | BaseConnector, website, third-party, Chilli POS adapters
| 3.3 | Raw Order Storage | RawOrder entity, deduplication, idempotency
| 3.4 | Ingestion Endpoints | Input validation, rate limiting, error handling
| 3.5 | Ingestion Tests | Connector tests, dedup, integration, high-concurrency
WEEK 4: May 20 - May 26
| 4.1 | Order Normalization | Canonical model, normalization service, errors, queue
| 4.2 | Branch Routing | Routing service, location mapping, decisions
| 4.3 | Lifecycle Management | Order states, actions, status endpoints
| 4.4 | Processing Tests | Normalization, routing, lifecycle, high-load
| 4.5 | Order Endpoints | Query endpoints, analytics
WEEK 5: May 27 - Jun 2
| 5.1 | Socket.IO Setup | Server config, auth, events, rooms
| 5.2 | FCM Integration | Firebase config, token management, push service
| 5.3 | Notification Orchestrator | Event handling, queue management, status tracking
| 5.4 | Escalation Engine | Retry policy (10-30s), escalation (60-120s), manager notify
| 5.5 | Notification Tests | Socket.IO, FCM, escalation, high-concurrency
WEEK 6: Jun 3 - Jun 9
| 6.1 | Next.js Setup | Project init, auth integration, API client
| 6.2 | Order Management | Live feed, order details, filtering/search
| 6.3 | Print System | Print service, auto-print, reprint, configuration
| 6.4 | Analytics & Monitoring | Order analytics, user/branch performance, system health
| 6.5 | Role-Based Views | Super Admin, Branch Manager, Kitchen/Staff views
| 6.6 | Dashboard Tests | Component, integration, E2E tests
WEEK 7: Jun 10 - Jun 16
| 7.1 | React Native Setup | Project init, auth, API client for iOS/Android
| 7.2 | Real-Time Notifications | Socket.IO client, FCM setup, notification UI
| 7.3 | Order Management | Queue screen, order details, recent orders
| 7.4 | Print Functionality | Auto-print, reprint, printer selection
| 7.5 | User Management | Profile, branch switching, logout
| 7.6 | Mobile Tests | Unit, component, integration, performance
WEEK 8: Jun 17 - Jun 23
| 8.1 | Production Setup | Docker images, docker-compose prod, backups, monitoring
| 8.2 | System Testing | Load test (100+/sec), chaos engineering, security, E2E
| 8.3 | Documentation | API docs, runbooks, architecture, developer guide
| 8.4 | Optimization | DB queries, API response, frontend performance, queue
| 8.5 | Final QA | UAT, regression, performance targets, readiness checklist
| 8.6 | Go-Live | Production deploy, monitoring, communication, optimization